# Session Report — Rigveda Samhitā Translation Project

Prepared for Bhargavi Upadhya. Covers the work of the long working session that took Volume 1 to completion, built the review tooling, cross-checked Volume 2 against a second scan, and began Volume 6.

Repository: bhargaviupa/rik-translation · Working branch: claude/modest-ptolemy-9efv8s

## 1. Where things stand

| Volume | Content | Status |
| --- | --- | --- |
| 1 | Front matter, Sūktas 1–2 (+ gaps A–D) | Complete; print PDF (1,249 pp.) and Word built |
| 2 | Sūktas 3–19 | Complete; PDF (1,217 pp.) and Word rebuilt; partly cross-checked against second scan |
| 3 | Sūktas 20–32 | Complete; PDF (799 pp.) and Word |
| 4 | Sūktas 33–46 | Complete; PDF (872 pp.) and Word |
| 5 | Sūktas 47–61 + Pariśiṣṭa | Complete; PDF (1,031 pp.) and Word |
| 6 | Sūktas 62–80 (Rig_Vol6.pdf, 638 pp.) | In progress — Sūkta 62 translated through printed p. 28 |

Volume 6 position: Sūkta 62, Rik 62.5, Special Topics; next page is printed p. 29 (PDF 47). Printed page = PDF − 18. Sūkta 62 has 13 Riks and runs to about printed p. 60.

## 2. What was done, in order

### 2.1 Volume 1 gaps

- Translated the four portions the draft had skipped (printed pp. 95–167, 191–205, 261–283, 288–295) into Rigveda_Samhita_Vol1_Gaps_English_Translation.md (Gaps A–D).

- Integrated them into the print pipeline (publish/vol1_clean.py: load_gap, gap notices replaced by the translated text; chapters renumbered to the original contents table).

- Rebuilt Volume 1 PDF (now 1,249 pp.). Merged to main (PR #4).

### 2.2 Consolidated review spreadsheet

- Collected every [?] point across all volumes into publish/review/All_volumes_review_worklist.xlsx (9,832 rows: Vol 1 989, Vol 2 3,452, Vol 3 1,287, Vol 4 2,210, Vol 5 1,894, plus an “Other review points” sheet).

- Tools: publish/review_list.py, publish/review_all.py.

- You decided to review the spreadsheet yourself, so it was not regenerated after the Volume 2 edits.

### 2.3 Word files

- .docx files for all five volumes rebuilt and pushed so the PDFs and Word files are in sync (Volume 1 from a cleaned temporary copy; Volume 2 from the lightened-bold text; Devanagari counts checked).

### 2.4 Second-scan cross-check of Volume 2

- You supplied a second scan (Rig_Vol2_B.pdf, 128 MB). GitHub rejected the plain push (100 MB limit), so it lives on branch scan-b via Git LFS.

- Compared pages against the first scan; corrected misread words and numerals where the second scan was clearer (log: publish/review/vol2_xcheck_log.tsv; tools xcheck.py, xedit.py, halves.sh, flags.py).

- Coverage is partial (about pp. 31–74 and a few other pages). Roughly 3,268 [?] marks remain in Volume 2.

- You then chose to review everything yourself.

### 2.5 Volume 2, page 2 (Anuvāka table)

- Reconstructed the 24-row table of Anuvākas using your transcribed rows plus constraint arithmetic (contiguous Sūkta ranges, row sums, stated totals). Result: 24 Anuvākas, 191 Sūktas, 2,006 Riks. Rows 21–24 are marked [?] (see To-do).

- A wrong first row (“1–9, 70”) was corrected to 1: Sūktas 1–3 / 3 / 30.

### 2.6 Lighter bold in print and Word

- Heavy bold in the Volume 2 output was reduced (option 2 chosen): bold kept for section labels and the leading headword of a gloss; other inline bold removed. Implemented in publish/lighten.py, applied in publish/vol2_clean.py. The source .md is untouched.

- Volume 2 PDF and Word rebuilt. (Offered but not requested for Volumes 1, 3, 4, 5.)

### 2.7 Housekeeping

- main merged with the work above (PR #4, PR #5).

- CLAUDE.md updated (Volume 6 line, Publication-build status).

- A 3.3 GB .nsf file cannot be pushed to GitHub — discussion closed at your request.

### 2.8 Volume 6 set-up and translation

- Set up Rigveda_Samhita_Vol6_English_Translation.md: header, contents table of Sūktas 62–80, abbreviation table copied from Volume 5, offset PDF − 18.

- Sūkta 62 (ṛṣi Nodhā Gautama, Triṣṭubh, Indra; Anukramaṇī count 13 Riks) translated through printed p. 28:

  - pp. 1–15: Riks 62.1–62.2 complete; Rik 62.3 Saṃhitā → Bhāvārtha; Special Topics begin (Saramā and the Paṇis).

  - pp. 16–19: the Saramā–Paṇi dialogue (Ṛ. Saṃ. 10-108, as printed in Kannada script) with the source’s Kannada paraphrase; the “Paṇi” word-list (forms only); grammar note.

  - pp. 20–22: grammar notes for Rik 62.3 words; Rik 62.4 Saṃhitā, Pada, bhāṣya.

  - pp. 23–25: Rik 62.4 Pratipadārtha, Bhāvārtha, source’s English, Special Topics (navagva/daśagva; Ṛ. Saṃ. 10-62-6, 3-39-5, 10-14-6, 4-51-4); grammar page begins.

  - pp. 26–28: Rik 62.4 grammar concluded; Rik 62.5 Saṃhitā, Pada, bhāṣya, Pratipadārtha, Bhāvārtha, English; Special Topics begin.

- All committed and pushed to claude/modest-ptolemy-9efv8s.

## 3. Remarks and open flags

### 3.1 Volume 6, Sūkta 62 (translator’s flags)

- Nirukta references on several pages are small numerals — marked [?].

- Ṛgveda reference numerals on pp. 15–19 and 24–28 are marked [?]; the Paṇi word-list on pp. 18–19 gives the forms but not the reference numerals (too small and crowded).

- The first reference numerals of the citation “yenā navagve dadhyaṅ apornute…” (p. 24) are unreadable (written 9-10?-4 [?]).

- The verses on p. 16 are given as printed, which differs from the standard text in a few letters; I did not “correct” them. Doubtful letters: “भवामि” (standard: भवाति), “ने” for “न”, “अधुष्को”.

- Doubtful bhāṣya words in Rik 62.5 (p. 27): “उपक्षयितरिन्द्र” and “उपरमुप्तं”.

- Grammar pages (pp. 13–14, 19, 20, 22, 26, 27–28) are characterized, not transcribed; sūtra numbers are given only where legible and are tentative. Page 20 grammar note was written from a 150 dpi view only and is the least reliable of these.

- Accent marks in the Saṃhitā/Pada are not reproduced (Kannada notation not convertible).

- English glosses of untranslated Ṛgveda quotations are labelled “mine and tentative”.

- The abbreviation key in the Volume 6 header was copied from Volume 5 and must be checked against PDF 18.

- Page headers’ small numerals (Aṣṭaka/Adhyāya/Varga) are unreliable and recorded as read.

### 3.2 Volume 2

- 3,268 [?] points still open (cross-check covered only ~26+ pages).

- Anuvāka table rows 21–24 ([?]): 21: 140–151 / 12 / 91; 22: 152–158 / 7 / 40; 23: 159–173 / 15 / 197; 24: 174–191 / 18 / 153.

- A stray Cyrillic string and old mid-file progress notes remain in the closed Volume 2 file; varga numerals unreconciled with colophons.

### 3.3 Volume 1

- The mantra index is omitted (unfinished in the draft).

- Rishi index: Kannada-numeral hymn references not reproduced; Jaiminīya and per-prapāṭhaka tables (pp. 117–118, 138–139, 150–151) not reproduced — each noted in the text.

- Needs outside Vedic/Sanskrit expert review; ~59 best-effort places could be compiled into a “known limitations” appendix.

### 3.4 General

- Numeral reading (Kannada numerals, especially 2/3/7) is the main residual uncertainty. Constraint checks work for tables, not for isolated citation numbers.

- About 9,000 [?] readings across Volumes 1–5 await outside expert review.

## 4. To-do list

### Translation

- Continue Sūkta 62 from printed p. 29 (PDF 47) — Rik 62.5 Special Topics, then Riks 62.6–62.13 (to about p. 60).

- Sūktas 63–80, one Sūkta per session, following CLAUDE.md conventions.

- Check the abbreviation key against PDF 18 when first needed.

- Rebuild Volume 6 docx/PDF only when asked.

### Review and quality

- You: review the all-volumes spreadsheet and the Volume 2 corrections (do not regenerate the worklist unless you ask).

- Finish the Volume 2 second-scan cross-check: pp. 1–30 and 75+ untouched; verify rows 21–24 of the p. 2 table against the print.

- Optional: use the second scan (or a third source) for Volumes 3–5 numerals.

- Outside expert review of [?] readings; known-limitations appendix for Volumes 1–2.

### Publication

- Present-day Maharaja and Guruji portraits, names, captions and permissions (reserved page in each volume).

- Optionally apply the bold-lightening to Volumes 1, 3, 4, 5 PDFs/Word (offered, not requested).

- Vol 1 mantra index (currently omitted).

- For Volume 6, when built: run publish/build_vol45.py-style build, then voice.residual() on its notes and add new phrases to voice.EXACT.

### Repository

- main does not yet contain the Volume 6 work — merge when you decide (the last merge, PR #5, predates Volume 6).

- The scan-b branch holds the 128 MB second scan via Git LFS — keep or remove when the cross-check is finished.

## 5. How to resume (new chat)

Continue the Volume 6 translation. Read CLAUDE.md and the last ~40 lines of Rigveda_Samhita_Vol6_English_Translation.md first. Work on branch claude/modest-ptolemy-9efv8s. Position: Sūkta 62, Rik 62.5, Special Topics, printed p. 29 (PDF 47) is next (printed page = PDF − 18). Source: Rig_Vol6.pdf. Follow the conventions in CLAUDE.md. Append only, replacing the single trailing “Progress note”; batches of 3 pages; commit and push after each batch. Don’t create a PR or rebuild docx/PDF unless asked.

## 6. Working conventions (reminder)

- View every page image before writing; never complete Sanskrit from memory.

- Sanskrit always in three layers: Devanagari + IAST + English.

- Mark doubtful readings and numerals with [?]; never invent sūtra numbers.

- The source’s own English is reproduced as printed, with [sic] for misprints.

- Grammar pages (Vyākaraṇa-prakriyā) get a short note, not a transcription.

- One Sūkta per session; append-only output file with exactly one trailing progress note.